## Simplified
Milestone 1 | [17 empty] | Milestone 2 | [6 empty] | Milestone 3 | [9 empty] | Milestone 4
Due May 21, 2021 | [17 empty] | Due May 28, 2021 | [6 empty] | Due June 7, 2021 | [9 empty] | Due June 28, 2021
MVP for Python package visualizations and metrics (5 functions) | [17 empty] | MVP for UI, first round of package improvements | [6 empty] | MVP for stretch goal, first round improvements for UI | [9 empty] | Report and touch-ups for previous milestones
May | [27 empty] | June
 | time axis 2021-05-04 to 2021-06-26
 | time axis 2021-05-04 to 2021-06-26
Background Research
Main Goal: metrics and visualization Python package
Main Goal: interactive User Interface
Stretch Goal: Machine Learning
Proposal Report & Presentation
Final Report & Presentation

## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Green
SimPL EEG Capstone
Company name | MDS
Project lead | Joel
Project start date: | 2021-05-03 | [10 empty] | Scrolling increment: | [5 empty] | 1
Milestone marker: | 1 | 1 |  |  | May | [27 empty] | June
 | time axis 2021-05-04 to 2021-06-28
Milestone description | Assigned to | Progress | Start | Days | time axis 2021-05-04 to 2021-06-28
Deadlines
Proposal Presentation |  |  | 2021-05-07 | 1 | bar: 2021-05-07
Proposal Report |  |  | 2021-05-14 | 1 | bar: 2021-05-14
Final Presentation |  |  | 2021-06-17 | 1 | bar: 2021-06-17
Report draft |  |  | 2021-06-22 | 1 | bar: 2021-06-22
Final Report |  |  | 2021-06-28 | 1 | bar: 2021-06-28
Teamwork Reflection |  |  | 2021-06-29 | 1
Main Goal: Python package
Research - EEG background, existing python packages |  |  | 2021-05-03 | 7 | bar: 2021-05-04 to 2021-05-08
Python package - metrics and visualiizations |  |  | 2021-05-03 | 30 | bar: 2021-05-04 to 2021-05-31
Stretch Goal 1: User Interface |  |  | 2021-05-18 | 25 | bar: 2021-05-19 to 2021-06-10
Stretch Goal 3: ML Classification |  |  | 2021-05-28 | 21 | bar: 2021-05-29 to 2021-06-16
Proposal Presentation and Report |  |  | 2021-05-04 | 12 | bar: 2021-05-05 to 2021-05-14
Final Presentation and Report |  |  | 2021-06-07 | 21 | bar: 2021-06-08 to 2021-06-26
To add more data, Insert new rows ABOVE this one

## Blue
Project title
Company name
Project lead
Project start date: | 2021-05-10 | [10 empty] | Scrolling increment: | [5 empty] | 13
Milestone marker: | 1 | 1 |  |  | May | [13 empty] | June | [27 empty] | July
 | time axis 2021-05-23 to 2021-07-17
Milestone description | Assigned to | Progress | Start | Days | time axis 2021-05-23 to 2021-07-17
Title 1
Task 1 |  | 25% | 2021-05-13 | 3
Task 2 |  |  | 2021-05-18 | 1
Task 3 |  | 50% | 2021-05-10 | 10
Task 4 |  |  | 2021-06-02 | 1 | bar: 2021-06-02
Task 5 |  | 10% | 2021-05-19 | 6
Title 2
Task 1 |  | 60% | 2021-05-19 | 13
Task 2 |  | 50% | 2021-05-20 | 9
Task 3 |  | 33% | 2021-05-28 | 11
Task 4 |  |  | 2021-06-06 | 1 | bar: 2021-06-06
Task 5 |  |  | 2021-06-07 | 24
Title 3
Task 1 |  |  | 2021-05-28 | 4
Task 2 |  |  | 2021-06-01 | 14
Task 3 |  |  | 2021-06-17 | 6
Task 4 |  |  | 2021-06-30 | 3
Task 5 |  |  | 2021-06-22 | 19
Title 4
Task 1 |  |  | 2021-06-19 | 15
Task 2 |  |  | 2021-06-11 | 5
Task 3 |  |  | 2021-08-01 | 5
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Purple
Project title
Company name
Project lead
Project start date: | 2021-05-10 | [10 empty] | Scrolling increment: | [5 empty] | 13
Milestone marker: | 1 | 1 |  |  | May | [13 empty] | June | [27 empty] | July
 | time axis 2021-05-23 to 2021-07-17
Milestone description | Assigned to | Progress | Start | Days | time axis 2021-05-23 to 2021-07-17
Title 1
Task 1 |  | 25% | 2021-05-13 | 3
Task 2 |  |  | 2021-05-18 | 1
Task 3 |  | 50% | 2021-05-10 | 10
Task 4 |  |  | 2021-06-02 | 1 | bar: 2021-06-02
Task 5 |  | 10% | 2021-05-19 | 6
Title 2
Task 1 |  | 60% | 2021-05-19 | 13
Task 2 |  | 50% | 2021-05-20 | 9
Task 3 |  | 33% | 2021-05-28 | 11
Task 4 |  |  | 2021-06-06 | 1 | bar: 2021-06-06
Task 5 |  |  | 2021-06-07 | 24
Title 3
Task 1 |  |  | 2021-05-28 | 4
Task 2 |  |  | 2021-06-01 | 14
Task 3 |  |  | 2021-06-17 | 6
Task 4 |  |  | 2021-06-30 | 3
Task 5 |  |  | 2021-06-22 | 19
Title 4
Task 1 |  |  | 2021-06-19 | 15
Task 2 |  |  | 2021-06-11 | 5
Task 3 |  |  | 2021-08-01 | 5
Task 4
Task 5
To add more data, Insert new rows ABOVE this one